## Calendar
MILESTONE CALENDAR
Website launch ¦ October 2027
Change the year and month on Milestones. Completed items stay visible; cancelled items are excluded.
Each day shows up to 3 milestones. “More” points to the full Milestones list. [Complete] identifies finished work.
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2027-09-27 | 2027-09-28 | 2027-09-29 | 2027-09-30 | 2027-10-01 | 2027-10-02 | 2027-10-03
2027-10-04 | 2027-10-05 | 2027-10-06 | 2027-10-07 | 2027-10-08 | 2027-10-09 | 2027-10-10
| Scope agreed [Complete] |  |  | Design signed off [Complete]
2027-10-11 | 2027-10-12 | 2027-10-13 | 2027-10-14 | 2027-10-15 | 2027-10-16 | 2027-10-17
Content approved
2027-10-18 | 2027-10-19 | 2027-10-20 | 2027-10-21 | 2027-10-22 | 2027-10-23 | 2027-10-24
| Security review |  |  | UAT signed off
2027-10-25 | 2027-10-26 | 2027-10-27 | 2027-10-28 | 2027-10-29 | 2027-10-30 | 2027-10-31
| Training complete |  | Go / no-go decision |  | Launch
Support handover
Launch communications
+ 1 more in list
2027-11-01 | 2027-11-02 | 2027-11-03 | 2027-11-04 | 2027-11-05 | 2027-11-06 | 2027-11-07
Red text = overdue unfinished milestone. Highlighted date = today. Dates outside the selected month have no entries.
stakeholdermap.com ¦ Excel project calendars

## Year overview
YEAR OVERVIEW
Website launch ¦ 2027
Coloured dates have milestones. Red dates include overdue work. Completed milestones remain included.
JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | FEBRUARY | FEBRUARY | FEBRUARY | FEBRUARY | FEBRUARY | FEBRUARY | FEBRUARY | MARCH | MARCH | MARCH | MARCH | MARCH | MARCH | MARCH
M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  |  |  | 2027-01-01 | 2027-01-02 | 2027-01-03 | 2027-02-01 | 2027-02-02 | 2027-02-03 | 2027-02-04 | 2027-02-05 | 2027-02-06 | 2027-02-07 | 2027-03-01 | 2027-03-02 | 2027-03-03 | 2027-03-04 | 2027-03-05 | 2027-03-06 | 2027-03-07
2027-01-04 | 2027-01-05 | 2027-01-06 | 2027-01-07 | 2027-01-08 | 2027-01-09 | 2027-01-10 | 2027-02-08 | 2027-02-09 | 2027-02-10 | 2027-02-11 | 2027-02-12 | 2027-02-13 | 2027-02-14 | 2027-03-08 | 2027-03-09 | 2027-03-10 | 2027-03-11 | 2027-03-12 | 2027-03-13 | 2027-03-14
2027-01-11 | 2027-01-12 | 2027-01-13 | 2027-01-14 | 2027-01-15 | 2027-01-16 | 2027-01-17 | 2027-02-15 | 2027-02-16 | 2027-02-17 | 2027-02-18 | 2027-02-19 | 2027-02-20 | 2027-02-21 | 2027-03-15 | 2027-03-16 | 2027-03-17 | 2027-03-18 | 2027-03-19 | 2027-03-20 | 2027-03-21
2027-01-18 | 2027-01-19 | 2027-01-20 | 2027-01-21 | 2027-01-22 | 2027-01-23 | 2027-01-24 | 2027-02-22 | 2027-02-23 | 2027-02-24 | 2027-02-25 | 2027-02-26 | 2027-02-27 | 2027-02-28 | 2027-03-22 | 2027-03-23 | 2027-03-24 | 2027-03-25 | 2027-03-26 | 2027-03-27 | 2027-03-28
2027-01-25 | 2027-01-26 | 2027-01-27 | 2027-01-28 | 2027-01-29 | 2027-01-30 | 2027-01-31 | [7 empty] | 2027-03-29 | 2027-03-30 | 2027-03-31
APRIL | APRIL | APRIL | APRIL | APRIL | APRIL | APRIL | MAY | MAY | MAY | MAY | MAY | MAY | MAY | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE
M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  |  | 2027-04-01 | 2027-04-02 | 2027-04-03 | 2027-04-04 | [5 empty] | 2027-05-01 | 2027-05-02 |  | 2027-06-01 | 2027-06-02 | 2027-06-03 | 2027-06-04 | 2027-06-05 | 2027-06-06
2027-04-05 | 2027-04-06 | 2027-04-07 | 2027-04-08 | 2027-04-09 | 2027-04-10 | 2027-04-11 | 2027-05-03 | 2027-05-04 | 2027-05-05 | 2027-05-06 | 2027-05-07 | 2027-05-08 | 2027-05-09 | 2027-06-07 | 2027-06-08 | 2027-06-09 | 2027-06-10 | 2027-06-11 | 2027-06-12 | 2027-06-13
2027-04-12 | 2027-04-13 | 2027-04-14 | 2027-04-15 | 2027-04-16 | 2027-04-17 | 2027-04-18 | 2027-05-10 | 2027-05-11 | 2027-05-12 | 2027-05-13 | 2027-05-14 | 2027-05-15 | 2027-05-16 | 2027-06-14 | 2027-06-15 | 2027-06-16 | 2027-06-17 | 2027-06-18 | 2027-06-19 | 2027-06-20
2027-04-19 | 2027-04-20 | 2027-04-21 | 2027-04-22 | 2027-04-23 | 2027-04-24 | 2027-04-25 | 2027-05-17 | 2027-05-18 | 2027-05-19 | 2027-05-20 | 2027-05-21 | 2027-05-22 | 2027-05-23 | 2027-06-21 | 2027-06-22 | 2027-06-23 | 2027-06-24 | 2027-06-25 | 2027-06-26 | 2027-06-27
2027-04-26 | 2027-04-27 | 2027-04-28 | 2027-04-29 | 2027-04-30 |  |  | 2027-05-24 | 2027-05-25 | 2027-05-26 | 2027-05-27 | 2027-05-28 | 2027-05-29 | 2027-05-30 | 2027-06-28 | 2027-06-29 | 2027-06-30
2027-05-31
JULY | JULY | JULY | JULY | JULY | JULY | JULY | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER
M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
JULY: 2027-07-01; JULY: 2027-07-02; JULY: 2027-07-03; JULY: 2027-07-04 | [6 empty] | 2027-08-01 |  |  | 2027-09-01 | 2027-09-02 | 2027-09-03 | 2027-09-04 | 2027-09-05
2027-07-05 | 2027-07-06 | 2027-07-07 | 2027-07-08 | 2027-07-09 | 2027-07-10 | 2027-07-11 | 2027-08-02 | 2027-08-03 | 2027-08-04 | 2027-08-05 | 2027-08-06 | 2027-08-07 | 2027-08-08 | 2027-09-06 | 2027-09-07 | 2027-09-08 | 2027-09-09 | 2027-09-10 | 2027-09-11 | 2027-09-12
2027-07-12 | 2027-07-13 | 2027-07-14 | 2027-07-15 | 2027-07-16 | 2027-07-17 | 2027-07-18 | 2027-08-09 | 2027-08-10 | 2027-08-11 | 2027-08-12 | 2027-08-13 | 2027-08-14 | 2027-08-15 | 2027-09-13 | 2027-09-14 | 2027-09-15 | 2027-09-16 | 2027-09-17 | 2027-09-18 | 2027-09-19
2027-07-19 | 2027-07-20 | 2027-07-21 | 2027-07-22 | 2027-07-23 | 2027-07-24 | 2027-07-25 | 2027-08-16 | 2027-08-17 | 2027-08-18 | 2027-08-19 | 2027-08-20 | 2027-08-21 | 2027-08-22 | 2027-09-20 | 2027-09-21 | 2027-09-22 | 2027-09-23 | 2027-09-24 | 2027-09-25 | 2027-09-26
2027-07-26 | 2027-07-27 | 2027-07-28 | 2027-07-29 | 2027-07-30 | 2027-07-31 |  | 2027-08-23 | 2027-08-24 | 2027-08-25 | 2027-08-26 | 2027-08-27 | 2027-08-28 | 2027-08-29 | 2027-09-27 | 2027-09-28 | 2027-09-29 | 2027-09-30
[7 empty] | 2027-08-30 | 2027-08-31
OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER
M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  |  |  | 2027-10-01 | 2027-10-02 | 2027-10-03 | 2027-11-01 | 2027-11-02 | 2027-11-03 | 2027-11-04 | 2027-11-05 | 2027-11-06 | 2027-11-07 |  |  | 2027-12-01 | 2027-12-02 | 2027-12-03 | 2027-12-04 | 2027-12-05
2027-10-04 | 2027-10-05 | 2027-10-06 | 2027-10-07 | 2027-10-08 | 2027-10-09 | 2027-10-10 | 2027-11-08 | 2027-11-09 | 2027-11-10 | 2027-11-11 | 2027-11-12 | 2027-11-13 | 2027-11-14 | 2027-12-06 | 2027-12-07 | 2027-12-08 | 2027-12-09 | 2027-12-10 | 2027-12-11 | 2027-12-12
2027-10-11 | 2027-10-12 | 2027-10-13 | 2027-10-14 | 2027-10-15 | 2027-10-16 | 2027-10-17 | 2027-11-15 | 2027-11-16 | 2027-11-17 | 2027-11-18 | 2027-11-19 | 2027-11-20 | 2027-11-21 | 2027-12-13 | 2027-12-14 | 2027-12-15 | 2027-12-16 | 2027-12-17 | 2027-12-18 | 2027-12-19
2027-10-18 | 2027-10-19 | 2027-10-20 | 2027-10-21 | 2027-10-22 | 2027-10-23 | 2027-10-24 | 2027-11-22 | 2027-11-23 | 2027-11-24 | 2027-11-25 | 2027-11-26 | 2027-11-27 | 2027-11-28 | 2027-12-20 | 2027-12-21 | 2027-12-22 | 2027-12-23 | 2027-12-24 | 2027-12-25 | 2027-12-26
2027-10-25 | 2027-10-26 | 2027-10-27 | 2027-10-28 | 2027-10-29 | 2027-10-30 | 2027-10-31 | 2027-11-29 | 2027-11-30 | [5 empty] | 2027-12-27 | 2027-12-28 | 2027-12-29 | 2027-12-30 | 2027-12-31

## Milestones
PROJECT MILESTONES
Start here: replace the examples below. Edit coloured input cells; calculated columns update automatically.
Project name | Website launch |  | Review date | 2026-10-13
Calendar year | 2027 |  | Month (1–12) | 10
Enter up to 200 milestones (rows 11–210). Keep titles short. Filter this list to see every item on a busy date.
Milestone | Due date | Owner | Workstream | Status | Notes / acceptance | Timing | Calendar key | Team names (edit)
Scope agreed | 2027-10-05 | Alex | Planning | Complete | Sponsor accepts the scope. | Complete | 46665001 | Alex
Design signed off | 2027-10-08 | Sam | Design | Complete | Design approval recorded. | Complete | 46668001 | Sam
Content approved | 2027-10-14 | Jo | Content | In progress | All launch copy approved. | Upcoming | 46674001 | Jo
Security review | 2027-10-19 | Alex | Technology | At risk | Resolve outstanding findings. | Upcoming | 46679001
UAT signed off | 2027-10-22 | Sam | Technology | Planned | Business users accept the release. | Upcoming | 46682001
Training complete | 2027-10-26 | Jo | People | Planned | Support team trained. | Upcoming | 46686001
Go / no-go decision | 2027-10-28 | Alex | Governance | Planned | Sponsor confirms readiness. | Upcoming | 46688001
Launch | 2027-10-30 | Sam | Technology | Planned | Production release verified. | Upcoming | 46690001
Support handover | 2027-10-30 | Jo | People | Planned | Operational ownership accepted. | Upcoming | 46690002
Launch communications | 2027-10-30 | Alex | Content | Planned | Customer announcement sent. | Upcoming | 46690003
Benefits baseline | 2027-10-30 | Jo | Governance | Planned | Baseline measures recorded. | Upcoming | 46690004
First benefits review | 2027-11-20 | Alex | Governance | Planned | Review adoption and support demand. | Upcoming | 46711001
Project closure | 2027-12-04 | Sam | Governance | Planned | Agree closure report. | Upcoming | 46725001
Discovery complete | 2027-09-18 | Jo | Planning | Complete | Research findings accepted. | Complete | 46648001

## Resources
PROJECT RESOURCES
Practical guides and templates from stakeholdermap.com
Click a resource title to open its web page, where you can read more and find downloads.
RESOURCE | HOW IT HELPS | WEBSITE
Milestone list template | Describe key checkpoints, their dates and whether they are mandatory. | stakeholdermap.com
Project management templates | Browse the full collection of Excel, Word and PDF templates. | stakeholdermap.com
Activity list template | List the activities needed to deliver your project milestones. | stakeholdermap.com
Activity attributes template | Add scheduling details, resource needs and dependencies to activities. | stakeholdermap.com
WBS dictionary template | Define deliverables, owners, milestones and acceptance criteria. | stakeholdermap.com
Project status report | Report milestone progress alongside the wider project status. | stakeholdermap.com
Project charter template | Agree the project objectives and initial milestone schedule. | stakeholdermap.com
Project initiation document | Bring scope, milestones, dependencies and project controls together. | stakeholdermap.com
Visit stakeholdermap.com