## Calendar
MILESTONE CALENDAR
Website launch ¦ October 2026
Change the year and month on Milestones. Completed items stay visible; cancelled items are excluded.
Each day shows up to 3 milestones. “More” points to the full Milestones list. [Complete] identifies finished work.
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04
2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11
Scope agreed [Complete] |  |  | Design signed off [Complete]
2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18
Content approved
2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25
Security review |  |  | UAT signed off
2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01
Training complete |  | Go / no-go decision |  | Launch
Support handover
Launch communications
+ 1 more in list
2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08
Red text = overdue unfinished milestone. Highlighted date = today. Dates outside the selected month have no entries.
stakeholdermap.com ¦ Excel project calendars

## Year overview
YEAR OVERVIEW
Website launch ¦ 2026
Coloured dates have milestones. Red dates include overdue work. Completed milestones remain included.
JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | JANUARY | FEBRUARY | FEBRUARY | FEBRUARY | FEBRUARY | FEBRUARY | FEBRUARY | FEBRUARY | MARCH | MARCH | MARCH | MARCH | MARCH | MARCH | MARCH
M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
JANUARY: 2026-01-01; JANUARY: 2026-01-02; JANUARY: 2026-01-03; JANUARY: 2026-01-04 | [6 empty] | 2026-02-01 | [6 empty] | 2026-03-01
2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08
2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15
2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22
2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 |  | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 |  | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29
[14 empty] | 2026-03-30 | 2026-03-31
APRIL | APRIL | APRIL | APRIL | APRIL | APRIL | APRIL | MAY | MAY | MAY | MAY | MAY | MAY | MAY | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE | JUNE
M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 |  |  |  |  | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14
2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21
2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28
2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 |  |  |  | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-29 | 2026-06-30
JULY | JULY | JULY | JULY | JULY | JULY | JULY | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | AUGUST | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER | SEPTEMBER
M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | [5 empty] | 2026-08-01 | 2026-08-02 |  | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06
2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13
2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20
2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27
2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-09-28 | 2026-09-29 | 2026-09-30
2026-08-31
OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | OCTOBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | NOVEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER | DECEMBER
M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  |  | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | [6 empty] | 2026-11-01 |  | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06
2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13
2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20
2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27
2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 |  | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31
2026-11-30

## Milestones
PROJECT MILESTONES
Start here: replace the examples below. Edit coloured input cells; calculated columns update automatically.
Project name | Website launch |  | Review date | 2026-10-13
Calendar year | 2026 |  | Month (1–12) | 10
Enter up to 200 milestones (rows 11–210). Keep titles short. Filter this list to see every item on a busy date.
Milestone | Due date | Owner | Workstream | Status | Notes / acceptance | Timing | Calendar key | Team names (edit)
Scope agreed | 2026-10-05 | Alex | Planning | Complete | Sponsor accepts the scope. | Complete | 46300001 | Alex
Design signed off | 2026-10-08 | Sam | Design | Complete | Design approval recorded. | Complete | 46303001 | Sam
Content approved | 2026-10-14 | Jo | Content | In progress | All launch copy approved. | Due within 7 days | 46309001 | Jo
Security review | 2026-10-19 | Alex | Technology | At risk | Resolve outstanding findings. | Due within 7 days | 46314001
UAT signed off | 2026-10-22 | Sam | Technology | Planned | Business users accept the release. | Upcoming | 46317001
Training complete | 2026-10-26 | Jo | People | Planned | Support team trained. | Upcoming | 46321001
Go / no-go decision | 2026-10-28 | Alex | Governance | Planned | Sponsor confirms readiness. | Upcoming | 46323001
Launch | 2026-10-30 | Sam | Technology | Planned | Production release verified. | Upcoming | 46325001
Support handover | 2026-10-30 | Jo | People | Planned | Operational ownership accepted. | Upcoming | 46325002
Launch communications | 2026-10-30 | Alex | Content | Planned | Customer announcement sent. | Upcoming | 46325003
Benefits baseline | 2026-10-30 | Jo | Governance | Planned | Baseline measures recorded. | Upcoming | 46325004
First benefits review | 2026-11-20 | Alex | Governance | Planned | Review adoption and support demand. | Upcoming | 46346001
Project closure | 2026-12-04 | Sam | Governance | Planned | Agree closure report. | Upcoming | 46360001
Discovery complete | 2026-09-18 | Jo | Planning | Complete | Research findings accepted. | Complete | 46283001

## Resources
PROJECT RESOURCES
Practical guides and templates from stakeholdermap.com
Click a resource title to open its web page, where you can read more and find downloads.
RESOURCE | HOW IT HELPS | WEBSITE
Milestone list template | Describe key checkpoints, their dates and whether they are mandatory. | stakeholdermap.com
Project management templates | Browse the full collection of Excel, Word and PDF templates. | stakeholdermap.com
Activity list template | List the activities needed to deliver your project milestones. | stakeholdermap.com
Activity attributes template | Add scheduling details, resource needs and dependencies to activities. | stakeholdermap.com
WBS dictionary template | Define deliverables, owners, milestones and acceptance criteria. | stakeholdermap.com
Project status report | Report milestone progress alongside the wider project status. | stakeholdermap.com
Project charter template | Agree the project objectives and initial milestone schedule. | stakeholdermap.com
Project initiation document | Bring scope, milestones, dependencies and project controls together. | stakeholdermap.com
Visit stakeholdermap.com