## ACTIVITY ATTRIBUTES
ACTIVITY ATTRIBUTES
PROJECT No: | MA-015-02 | FULL PROJECT NAME: | Project Orion
LAST UPDATE: | 2021-07-21 | PROJECT MANAGER: | A Smith
ACTIVITY |  |  | ACTIVITY RESOURCE REQUIREMENTS |  |  |  |  | ACTIVITY SCHEDULE ATTRIBUTES
ACTIVITY ID | ACTIVITY TITLE | ACTIVITY DESCRIPTION | NUMBER AND TYPE OF TEAM RESOURCES REQUIRED | SKILL REQUIREMENTS | MATERIALS, SUPPLIES OR EQUIPMENT | TYPE OF EFFORT | RESOURCE LOCATIONS | IMPOSED DATES OR OTHER CONSTRAINTS | PREDECSSOR ACTIVITY IDs | RELATIONSHIP | LEAD OR LAG | SUCCESSOR ACTIVITY IDs | RELATIONSHIP | LEAD OR LAG
WBS1.2.1-A001 | Assign project manager | Send resource request to resource manager, who will identify the project manager. | One level 2 project manager | As for level 2 project manager description. Plus knowledge of kubernetes | None additional to standard (laptop etc). | 50% billable | US | Must be available from start of October | None | N/A | N/A | A002 | FS | 0
WBS1.2.1-A002 | Create Project record | Create project record in Project Management system | Project Manager | Knowledge of Project Management Method | None | Billable hrs (est. 2) | US | Complete on allocation to project | A001 | FS | 0 | A003 | FS | 0
WBS1.2.3-A003 | Assign project team | Book the project team in resource booking system. | Review SOW and create 1 resource booking for each project team member. Project Admin is booked separately via PMO. | Use Resource Booking system | None | Billable hrs (est. 2) | US | Complete on allocation to project | A002 | FS | 0 | A004 | FS | 3d lag

## DEFINITIONS
DEFINITIONS
PROJECT No.
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
This Link Takes You to Project No. in the Template
PROJECT MANAGER
The person responsible for the successful delivery of the project to time costs and quality constraints.
This Link Takes You to Project Manager in the Template
FULL PROJECT NAME
The name or title of the project.
This Link Takes You to the Full Project Name in the Template
LAST UPDATE
Date of the last update to this form.
This Link Takes You to Last Update
ACTIVITY ID
Give each activity a unique ID, this may include a reference to the work package in the work breakdown structure.
This Takes You to Activity ID in the Template
ACTIVITY TITLE
Give each activity a title that is as understandable as possible, in other words a title that the project team will understand.
This Link Takes You to Activity Title in the Template
ACTIVITY DESCRIPTION
Describe the activity clearly so that the person responsible understands the work.
This Link Takes You to Activity Description in the Template
RESOURCES REQUIRED
Enter the number and type of team resources required. For example, 2 developers.
This Link Takes You to Resources Required
SKILL REQUIREMENTS
Document the skills the team will need. For example, Java, C#, PHP or skill level such as senior or junior.
This Link Takes You to Skill Requirements
MATERIALS, SUPPLIES OR EQUIPMENT
Document any required resources that are not human.
This Link Takes You to Materials, Supplies or Equipment
TYPE OF EFFORT
How you will measure the effort required. For example, 4 days fixed duration or 4 days fixed effort.
This Link Takes You to Type of Effort
RESOURCE LOCATIONS
Note down where the work will take place.
This Link Takes You to Resources Locations
IMPOSED DATES OR OTHER CONSTRAINTS
Note any fixed dates or other constraints on the activity.
This Link Takes You to Imposed Dates or other Constraints
PREDECESSOR ACTIVITIES
Enter the activity IDs that need to be completed before this activity can start
This Link Takes You to Predecessor in the Template
RELATIONSHIPS
The type of dependency with the activity's predecessors. For example, start-to-start, finish-to-start.
Task dependencies in project planning.
This Link Takes You to Relationships
LEAD OR LAG
Any delay (lag) between the predecessor and this activity or any acceleration (lead).
This Link Takes You to Lead or Lag
SUCCESSOR ACTIVITIES
Enter any other activities that rely on the completion of this activity.
This Link Takes You to Successor in the Template
RELATIONSHIPS
The type of dependency with the activity's predecessors. For example, start-to-start, finish-to-start.
Task dependencies in project planning.
This Link Takes You to Relationships
LEAD OR LAG
Any delay (lag) between the predecessor and this activity or any acceleration (lead).
This Link Takes You to Lead or Lag
This template was provided by
https://www.stakeholdermap.com/

## Useful resources
Project Management resources
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel