## Summary
Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment
Summary of your impact register | Summary of your impact register | Summary of your impact register | Summary of your impact register | Summary of your impact register | Summary of your impact register | Summary of your impact register | Summary of your impact register | Summary of your impact register | Summary of your impact register | Summary of your impact register | Summary of your impact register | Summary of your impact register
Project / change | Project / change | Enter project name | Enter project name | Enter project name | Enter project name | Enter project name | Review date | Review date | 2026-11-07
Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot. | Start on Impact assessment. The worked example is separate. Replace the review date to take a fixed snapshot.
Impact records | Impact records | Impact records |  | High impact | High impact | High impact |  | Teams affected | Teams affected | Teams affected
0 |  |  |  | 0 |  |  |  | 0
Overdue actions | Overdue actions | Overdue actions |  | Open records | Open records | Open records |  | Details to complete | Details to complete | Details to complete
0 |  |  |  | 0 |  |  |  | 0
Impact levels | Impact levels | Impact levels | Impact levels | Impact levels | Impact levels |  | Actions | Actions | Actions | Actions | Actions | Actions
Level | Level | Level | Records | Open | Overdue |  | Status | Status | Status | Status | Records | Records
High | High | High | 0 | 0 | 0 |  | Not started | Not started | Not started | Not started | 0
Medium | Medium | Medium | 0 | 0 | 0 |  | In progress | In progress | In progress | In progress | 0
Low | Low | Low | 0 | 0 | 0 |  | Blocked | Blocked | Blocked | Blocked | 0
Not rated | Not rated | Not rated | 0 | 0 | 0 |  | Complete | Complete | Complete | Complete | 0
[7 empty] | Not required | Not required | Not required | Not required | 0
Open records include any entered row not marked Complete or Not required. | Open records include any entered row not marked Complete or Not required. | Open records include any entered row not marked Complete or Not required. | Open records include any entered row not marked Complete or Not required. | Open records include any entered row not marked Complete or Not required. | Open records include any entered row not marked Complete or Not required. |  | Not set | Not set | Not set | Not set | 0
Open records include any entered row not marked Complete or Not required. | Open records include any entered row not marked Complete or Not required. | Open records include any entered row not marked Complete or Not required. | Open records include any entered row not marked Complete or Not required. | Open records include any entered row not marked Complete or Not required. | Open records include any entered row not marked Complete or Not required.
Use the summary in your review | Use the summary in your review | Use the summary in your review | Use the summary in your review | Use the summary in your review | Use the summary in your review | Use the summary in your review | Use the summary in your review | Use the summary in your review | Use the summary in your review | Use the summary in your review | Use the summary in your review | Use the summary in your review
1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption.
1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption. | 1. Filter Impact level to High and confirm that the support matches the disruption.
2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date.
2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date. | 2. Filter Deadline to Overdue. Agree an owner, next action and revised date.
3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review.
3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review. | 3. Filter Missing details to nonblank. Fill the named fields before closing the review.
4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group.
4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group. | 4. Use consistent team names so the count treats each team as one group.
Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered.
Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered. | Amber fields are editable project details. Counts include all 200 prepared rows, even when the register is filtered.

## Impact assessment
Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment | Change impact assessment
Describe each change from the affected team’s point of view. | Describe each change from the affected team’s point of view. | Describe each change from the affected team’s point of view. | Describe each change from the affected team’s point of view. | Describe each change from the affected team’s point of view.
Capacity: 200 impact records | Capacity: 200 impact records | Capacity: 200 impact records | [5 empty] | Review date | 2026-11-07
Start in row 9. Use one row for each distinct impact on a team or group. | Start in row 9. Use one row for each distinct impact on a team or group. | Start in row 9. Use one row for each distinct impact on a team or group. | Start in row 9. Use one row for each distinct impact on a team or group. | Start in row 9. Use one row for each distinct impact on a team or group.
Enter details in B:L and O. Grey columns calculate automatically. Use the header filters to focus your review. | Enter details in B:L and O. Grey columns calculate automatically. Use the header filters to focus your review. | Enter details in B:L and O. Grey columns calculate automatically. Use the header filters to focus your review. | Enter details in B:L and O. Grey columns calculate automatically. Use the header filters to focus your review. | Enter details in B:L and O. Grey columns calculate automatically. Use the header filters to focus your review.
Impact ID | Affected team / group | Change area | Current way of working | What changes for me? | Impact level | Why this rating? | Support or action needed | Action owner | Action due | Action status | Deadline (auto) | Missing details (auto) | Evidence / notes | First team (auto)

## Worked example
Worked example: introducing a service desk | Worked example: introducing a service desk | Worked example: introducing a service desk | Worked example: introducing a service desk | Worked example: introducing a service desk
Fictional example. These records do not feed the Summary. | Fictional example. These records do not feed the Summary. | Fictional example. These records do not feed the Summary. | Fictional example. These records do not feed the Summary. | Fictional example. These records do not feed the Summary.
Example review date: 15 Mar 2027 | Example review date: 15 Mar 2027 | Example review date: 15 Mar 2027 | [6 empty] | 2027-03-15
Start in row 9. Use one row for each distinct impact on a team or group. | Start in row 9. Use one row for each distinct impact on a team or group. | Start in row 9. Use one row for each distinct impact on a team or group. | Start in row 9. Use one row for each distinct impact on a team or group. | Start in row 9. Use one row for each distinct impact on a team or group.
Enter details in B:L and O. Grey columns calculate automatically. Use the header filters to focus your review. | Enter details in B:L and O. Grey columns calculate automatically. Use the header filters to focus your review. | Enter details in B:L and O. Grey columns calculate automatically. Use the header filters to focus your review. | Enter details in B:L and O. Grey columns calculate automatically. Use the header filters to focus your review. | Enter details in B:L and O. Grey columns calculate automatically. Use the header filters to focus your review.
Impact ID | Affected team / group | Change area | Current way of working | What changes for me? | Impact level | Why this rating? | Support or action needed | Action owner | Action due | Action status | Deadline (auto) | Missing details (auto) | Evidence / notes | First team (auto)
CI-001 | Requesters | Process | Email a shared mailbox and chase for updates. | Submit requests through a portal and check progress there. | High | Every request follows a new route. Colleagues need practice before launch. | Run a short demonstration and publish a quick-start guide. | Alex Morgan | 2027-03-12 | In progress | Overdue |  | Pilot feedback is being added to the guide. | 1
CI-002 | Service desk | Technology | Copy emails into a shared spreadsheet. | Triage tickets in one queue and use agreed categories. | High | Daily work changes and incorrect routing could delay urgent requests. | Run practice sessions using common and urgent requests. | Sam Patel | 2027-03-17 | Blocked | Due in 7 days |  | Waiting for the test queue and training accounts. | 1
CI-003 | Team managers | Roles and responsibilities | Receive approval requests by email. | Approve requests in the portal and nominate a deputy. | Medium | The approval decision is familiar but the route and cover arrangements change. | Show managers how to approve and set up deputies. | Jamie Chen | 2027-03-15 | Not started | Due today |  | Deputy list agreed at the managers meeting. | 1
CI-004 | Requesters | Skills and knowledge | Ask the service desk where to find common guidance. | Search the knowledge base before raising a request. | Medium | People need to learn the search terms and where help is stored. | Publish the ten most common answers and test them with users. | Casey Taylor | 2027-03-20 | In progress | Due in 7 days |  | Six answers drafted. Four still need review. | 0
CI-005 | IT support | Technology | Support mailbox access and spreadsheet permissions. | Maintain portal roles, queue access and notification rules. | High | Access errors could stop requests reaching the right team. | Test permissions and agree support and recovery steps. | Jordan Evans | 2027-03-10 | Complete | Closed |  | Access test results and support guide accepted on 10 Mar 2027. | 1
CI-006 | Team managers | Process | Build monthly totals by reading the shared spreadsheet. | Use the portal report for volumes, response times and backlogs. | Medium | The measures need agreement before managers use the report. | Agree report definitions and explain the first monthly results. | Riley Brown | 2027-03-25 | Not started | On track |  | Draft definitions are ready for review. | 0
CI-007 | Service desk | Policy | Keep closed request emails in the shared mailbox. | Follow the agreed record retention process in the portal. | Medium | The team needs a clear deletion and retrieval process. | Confirm the retention rule and add it to team guidance. | Morgan Reed | 2027-03-22 | In progress | Due in 7 days |  | Records team review is booked. | 0
CI-008 | Facilities | Technology | Open the existing Helpdesk bookmark to check assigned jobs. | The bookmark opens the renamed portal. The job list and steps stay the same. | Low | Only the portal name and bookmark target change for this group. |  |  |  | Not required | Closed |  | Bookmark updated centrally. Facilities lead confirmed that no extra training is needed. | 1

## Instructions and resources
Instructions and resources | Instructions and resources | Instructions and resources | Instructions and resources | Instructions and resources | Instructions and resources | Instructions and resources | Instructions and resources | Instructions and resources
Set up your assessment | Set up your assessment | Set up your assessment | Set up your assessment | Set up your assessment | Set up your assessment | Set up your assessment | Set up your assessment | Set up your assessment
1. Name the change | 1. Name the change | 1. Name the change | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date.
1. Name the change | 1. Name the change | 1. Name the change | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date.
1. Name the change | 1. Name the change | 1. Name the change | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date. | Enter the project name on Summary. Review date starts at today and updates automatically. Type a date over it for a fixed review date.
2. Describe each impact | 2. Describe each impact | 2. Describe each impact | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group.
2. Describe each impact | 2. Describe each impact | 2. Describe each impact | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group.
2. Describe each impact | 2. Describe each impact | 2. Describe each impact | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group. | Start in row 9 of Impact assessment. Give each row a unique ID, such as CI-001. Use one row for each distinct impact on a team or group.
3. Write for the people affected | 3. Write for the people affected | 3. Write for the people affected | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working.
3. Write for the people affected | 3. Write for the people affected | 3. Write for the people affected | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working.
3. Write for the people affected | 3. Write for the people affected | 3. Write for the people affected | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working. | Use What changes for me? to explain the practical difference. Compare it with the current way of working.
4. Agree the impact level | 4. Agree the impact level | 4. Agree the impact level | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project.
4. Agree the impact level | 4. Agree the impact level | 4. Agree the impact level | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project.
4. Agree the impact level | 4. Agree the impact level | 4. Agree the impact level | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project. | Select Low, Medium or High and record why. Use the definitions below consistently across the project.
5. Assign support and follow up | 5. Assign support and follow up | 5. Assign support and follow up | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why.
5. Assign support and follow up | 5. Assign support and follow up | 5. Assign support and follow up | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why.
5. Assign support and follow up | 5. Assign support and follow up | 5. Assign support and follow up | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why. | Record the support or action, owner, due date and status. Add evidence when complete. Use Not required only when no action is needed and explain why.
6. Review and update | 6. Review and update | 6. Review and update | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses.
6. Review and update | 6. Review and update | 6. Review and update | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses.
6. Review and update | 6. Review and update | 6. Review and update | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses. | Review high impacts, overdue work and missing details with the affected teams. Update the action status as work progresses.
Impact levels | Impact levels | Impact levels | Impact levels | Impact levels | Impact levels | Impact levels | Impact levels | Impact levels
High | High | High | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support. | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support. | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support. | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support. | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support. | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support.
High | High | High | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support. | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support. | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support. | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support. | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support. | A major change to daily work, responsibilities or service delivery. People need substantial preparation, practice or support.
Medium | Medium | Medium | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed. | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed. | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed. | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed. | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed. | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed.
Medium | Medium | Medium | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed. | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed. | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed. | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed. | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed. | A noticeable change to a familiar process or tool. Targeted guidance, training or an adjustment to working practices is needed.
Low | Low | Low | A small change with limited disruption. A brief explanation or simple update is normally enough. | A small change with limited disruption. A brief explanation or simple update is normally enough. | A small change with limited disruption. A brief explanation or simple update is normally enough. | A small change with limited disruption. A brief explanation or simple update is normally enough. | A small change with limited disruption. A brief explanation or simple update is normally enough. | A small change with limited disruption. A brief explanation or simple update is normally enough.
Low | Low | Low | A small change with limited disruption. A brief explanation or simple update is normally enough. | A small change with limited disruption. A brief explanation or simple update is normally enough. | A small change with limited disruption. A brief explanation or simple update is normally enough. | A small change with limited disruption. A brief explanation or simple update is normally enough. | A small change with limited disruption. A brief explanation or simple update is normally enough. | A small change with limited disruption. A brief explanation or simple update is normally enough.
Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating.
Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating. | Impact measures the scale of the change for the affected group. A beneficial change can still have a high impact. Record the reason for the rating.
How the workbook works | How the workbook works | How the workbook works | How the workbook works | How the workbook works | How the workbook works | How the workbook works | How the workbook works | How the workbook works
Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed.
Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed. | Deadline compares Action due with Review date. Today is Due today. The next seven days are Due in 7 days. Complete and Not required are Closed.
Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed.
Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed. | Missing details lists fields still to complete. Duplicate IDs are flagged. Closing a record does not remove missing details. Add completion evidence or the reason no action is needed.
First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent.
First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent. | First team is an automatic count helper. It marks the first occurrence of each team with 1 so Summary counts each team once. Keep team names consistent.
The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together.
The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together. | The register supports 200 rows (9 to 208). Keep new records inside this area. Sort and filter using the table headers, so each complete record stays together.
Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names.
Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names. | Enter dates as dates, for example 15/03/2027. Keep the grey formula columns M, N and P. The worked example uses a fixed date and fictional names.
Related resources | Related resources | Related resources | Related resources | Related resources | Related resources | Related resources | Related resources | Related resources
Stakeholder analysis | Stakeholder analysis | Stakeholder analysis | Stakeholder analysis | Stakeholder analysis | Stakeholder analysis | Stakeholder analysis | Stakeholder analysis | Stakeholder analysis
https://www.stakeholdermap.com/stakeholder-analysis.php | https://www.stakeholdermap.com/stakeholder-analysis.php | https://www.stakeholdermap.com/stakeholder-analysis.php | https://www.stakeholdermap.com/stakeholder-analysis.php | https://www.stakeholdermap.com/stakeholder-analysis.php | https://www.stakeholdermap.com/stakeholder-analysis.php | https://www.stakeholdermap.com/stakeholder-analysis.php | https://www.stakeholdermap.com/stakeholder-analysis.php | https://www.stakeholdermap.com/stakeholder-analysis.php
Communications plan template | Communications plan template | Communications plan template | Communications plan template | Communications plan template | Communications plan template | Communications plan template | Communications plan template | Communications plan template
https://www.stakeholdermap.com/project-templates/communications-plan-template.php | https://www.stakeholdermap.com/project-templates/communications-plan-template.php | https://www.stakeholdermap.com/project-templates/communications-plan-template.php | https://www.stakeholdermap.com/project-templates/communications-plan-template.php | https://www.stakeholdermap.com/project-templates/communications-plan-template.php | https://www.stakeholdermap.com/project-templates/communications-plan-template.php | https://www.stakeholdermap.com/project-templates/communications-plan-template.php | https://www.stakeholdermap.com/project-templates/communications-plan-template.php | https://www.stakeholdermap.com/project-templates/communications-plan-template.php
Training plan template | Training plan template | Training plan template | Training plan template | Training plan template | Training plan template | Training plan template | Training plan template | Training plan template
https://www.stakeholdermap.com/project-templates/training-plan-template.php | https://www.stakeholdermap.com/project-templates/training-plan-template.php | https://www.stakeholdermap.com/project-templates/training-plan-template.php | https://www.stakeholdermap.com/project-templates/training-plan-template.php | https://www.stakeholdermap.com/project-templates/training-plan-template.php | https://www.stakeholdermap.com/project-templates/training-plan-template.php | https://www.stakeholdermap.com/project-templates/training-plan-template.php | https://www.stakeholdermap.com/project-templates/training-plan-template.php | https://www.stakeholdermap.com/project-templates/training-plan-template.php
Change management plan template | Change management plan template | Change management plan template | Change management plan template | Change management plan template | Change management plan template | Change management plan template | Change management plan template | Change management plan template
https://www.stakeholdermap.com/project-templates/change-management-plan-template.php | https://www.stakeholdermap.com/project-templates/change-management-plan-template.php | https://www.stakeholdermap.com/project-templates/change-management-plan-template.php | https://www.stakeholdermap.com/project-templates/change-management-plan-template.php | https://www.stakeholdermap.com/project-templates/change-management-plan-template.php | https://www.stakeholdermap.com/project-templates/change-management-plan-template.php | https://www.stakeholdermap.com/project-templates/change-management-plan-template.php | https://www.stakeholdermap.com/project-templates/change-management-plan-template.php | https://www.stakeholdermap.com/project-templates/change-management-plan-template.php
More project management templates | More project management templates | More project management templates | More project management templates | More project management templates | More project management templates | More project management templates | More project management templates | More project management templates
https://www.stakeholdermap.com/project-templates/project-management-templates.php | https://www.stakeholdermap.com/project-templates/project-management-templates.php | https://www.stakeholdermap.com/project-templates/project-management-templates.php | https://www.stakeholdermap.com/project-templates/project-management-templates.php | https://www.stakeholdermap.com/project-templates/project-management-templates.php | https://www.stakeholdermap.com/project-templates/project-management-templates.php | https://www.stakeholdermap.com/project-templates/project-management-templates.php | https://www.stakeholdermap.com/project-templates/project-management-templates.php | https://www.stakeholdermap.com/project-templates/project-management-templates.php