## Calendar
Launch & cutover calendar 2027
Example launch. Replace the sample entries. Replace sample inputs; lavender columns contain formulas.
Launch date and time |  | 2027-11-20 22:00 |  | Time zone (no conversion) |  | UTC
Calendar month (1–12) |  | 11 | Year | 2027 | As of (editable) | 2026-10-21
Open cutover steps |  | 9 | Mandatory readiness items not passed |  |  | 7
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
2027-11-01 | 2027-11-02 | 2027-11-03 | 2027-11-04 | 2027-11-05 | 2027-11-06 | 2027-11-07
2027-11-08 | 2027-11-09 | 2027-11-10 | 2027-11-11 | 2027-11-12 | 2027-11-13 | 2027-11-14
1 readiness due
2027-11-15 | 2027-11-16 | 2027-11-17 | 2027-11-18 | 2027-11-19 | 2027-11-20 | 2027-11-21
[5 empty] | 8 cutover steps | 1 cutover steps
1 readiness due |  | 1 readiness due | 1 readiness due | 2 readiness due | 1 readiness due
LAUNCH 22:00
2027-11-22 | 2027-11-23 | 2027-11-24 | 2027-11-25 | 2027-11-26 | 2027-11-27 | 2027-11-28
2027-11-29 | 2027-11-30 | 2027-12-01 | 2027-12-02 | 2027-12-03 | 2027-12-04 | 2027-12-05
2027-12-06 | 2027-12-07 | 2027-12-08 | 2027-12-09 | 2027-12-10 | 2027-12-11 | 2027-12-12
Dates show planned step starts and readiness deadlines. Filter the detail sheets to see the owners and actions.
Start here: set the launch time, replace sample rows, confirm owners and update status during cutover.

## Cutover
Cutover runbook
100 steps. Offsets are elapsed minutes from launch (negative = before). Dependencies are recorded, not automatically scheduled.
Launch date and time |  | 2027-11-20 22:00 |  | Overdue unfinished steps |  |  | 0
Enter actual dates AND times. Complete steps need an actual finish. Blank unused rows stay out of the calendar.
Step ID | Activity | Owner | Depends on ID | Offset (min) | Duration (min) | Planned start | Planned finish | Actual start | Actual finish | Status | Timing flag | Rollback ID | Evidence / notes
C01 | Open cutover bridge | Cutover lead |  | -120 | 15 | 2027-11-20 20:00 | 2027-11-20 20:15 |  |  | Not started | On plan |  | Confirm contacts and escalation route
C02 | Confirm go/no-go decision | Sponsor | C01 | -105 | 15 | 2027-11-20 20:15 | 2027-11-20 20:30 |  |  | Not started | On plan |  | Record decision in Readiness
C03 | Freeze changes and notify users | Comms lead | C02 | -90 | 15 | 2027-11-20 20:30 | 2027-11-20 20:45 |  |  | Not started | On plan |  | Confirm maintenance window
C04 | Take and verify backup | Operations | C03 | -75 | 30 | 2027-11-20 20:45 | 2027-11-20 21:15 |  |  | Not started | On plan | R01 | Retain restore point
C05 | Deploy release | Release lead | C04 | -45 | 30 | 2027-11-20 21:15 | 2027-11-20 21:45 |  |  | Not started | On plan | R02 | Record release version
C06 | Run smoke tests | Test lead | C05 | -15 | 15 | 2027-11-20 21:45 | 2027-11-20 22:00 |  |  | Not started | On plan | R02 | Evidence required before opening
C07 | Open service to users | Service owner | C06 | 0 | 15 | 2027-11-20 22:00 | 2027-11-20 22:15 |  |  | Not started | On plan | R02 | Launch milestone
C08 | Monitor critical transactions | Operations | C07 | 15 | 120 | 2027-11-20 22:15 | 2027-11-21 00:15 |  |  | Not started | On plan | R02 | Check service and business measures
C09 | Confirm hypercare handover | Support lead | C08 | 1440 | 30 | 2027-11-21 22:00 | 2027-11-21 22:30 |  |  | Not started | On plan |  | Agree support ownership
Formulas:
Planned start = IF([Activity]="","",IF(NOT(ISNUMBER([Offset (min)])),"",Calendar!$D5+[Offset (min)]/1440))
Planned finish = IF(OR([Activity]="",[Planned start]="",NOT(ISNUMBER([Duration (min)]))),"",[Planned start]+[Duration (min)]/1440)

## Readiness
Launch readiness
60 checks. Deadlines use calendar days before launch. Record evidence and a named decision owner.
Decision | Pending | Decision owner |  |  | Recorded at
A passed checklist is not a go decision. Record the decision, owner, timestamp and rationale below.
Check ID | Readiness requirement | Owner | Mandatory? | Days before launch | Due date | Result | Evidence / decision rationale | Deadline flag
Q01 | User acceptance signed off | Business owner | Yes | 7 | 2027-11-13 | Pending |  | Open
Q02 | Restore rehearsal passed | Operations | Yes | 5 | 2027-11-15 | Pending |  | Open
Q03 | Support team and rota confirmed | Support lead | Yes | 3 | 2027-11-17 | Pending |  | Open
Q04 | Communications approved | Comms lead | Yes | 2 | 2027-11-18 | Pending |  | Open
Q05 | Monitoring and alerts verified | Operations | Yes | 1 | 2027-11-19 | Pending |  | Open
Q06 | Rollback criteria agreed | Service owner | Yes | 1 | 2027-11-19 | Pending |  | Open
Q07 | Final go/no-go evidence ready | Cutover lead | Yes | 0 | 2027-11-20 | Pending |  | Open
Formulas:
Recorded at = IF(OR([Pending]="",NOT(ISNUMBER([Days before launch]))),"",INT(Calendar!$D5)-[Days before launch])

## Rollback
Rollback plan
Agree measurable triggers, decision deadlines and recovery evidence before cutover. Sample entries must be tailored.
Rollback decision authority |  | Service owner (replace)
Decision deadline = launch time + offset minutes. Keep recovery steps in execution order in each plan.
Plan ID | Trigger / threshold | Decision offset (min) | Decision deadline | Owner | Recovery action | Validation / success criteria | Decision / evidence | Status
R01 | Backup verification fails | -45 | 2027-11-20 21:15 | Operations | Stop deployment; retain current service | Verify existing service remains healthy | Record stop decision | Ready
R02 | Critical smoke test fails | -5 | 2027-11-20 21:55 | Release lead | Restore verified backup and previous release | Re-run critical tests and reconcile data | Record rollback authority and time | Draft
Formulas:
Decision deadline = IF(OR([Trigger / threshold]="",NOT(ISNUMBER([Decision offset (min)]))),"",Calendar!$D5+[Decision offset (min)]/1440)

## Resources
Related project templates
stakeholdermap.com
Deployment plan
Plan deployment scope, responsibilities and release activities.
https://www.stakeholdermap.com/agile-templates/deployment-plan-template.php
User acceptance report
Record acceptance evidence before the launch decision.
https://www.stakeholdermap.com/project-templates/user-acceptance-report-template.php
Decision log
Keep the rationale and approvals behind go/no-go decisions.
https://www.stakeholdermap.com/project-templates/decision-log-template.php
Issue log
Track cutover defects, owners and resolution actions.
https://www.stakeholdermap.com/project-templates/issue-log.php
Risk register
Record launch risks, mitigations and contingency actions.
https://www.stakeholdermap.com/risk/risk-register.php
Lessons learned
Capture improvements after hypercare and handover.
https://www.stakeholdermap.com/project-templates/lessons-learned-template.php