## Calendar
Procurement and supplier calendar
What must we order or agree now to avoid delays later?
Year | 2027 | Month (1-12) | 10 | Status as at | 2026-10-19
Package ID or All | All | Type an exact ID from Procurement, or All.
Overdue next steps | 0 | Overdue promises | 0 | Late delivery promises | 1
Dates are planning deadlines. Completed items stay visible; cancelled items are excluded.
Tender = issue + close. Evaluation = completion. Promises = current supplier dates and extra commitments.
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
2027-09-27 | 2027-09-28 | 2027-09-29 | 2027-09-30 | 2027-10-01 | 2027-10-02 | 2027-10-03
| Tender: 1 |  |  | Tender: 1
2027-10-04 | 2027-10-05 | 2027-10-06 | 2027-10-07 | 2027-10-08 | 2027-10-09 | 2027-10-10
Tender: 1
Evaluation: 1
Award / order: 1
Promises: 1
2027-10-11 | 2027-10-12 | 2027-10-13 | 2027-10-14 | 2027-10-15 | 2027-10-16 | 2027-10-17
Tender: 1
Evaluation: 1
Award / order: 1
Delivery required: 1
Inspection: 1
Promises: 1
2027-10-18 | 2027-10-19 | 2027-10-20 | 2027-10-21 | 2027-10-22 | 2027-10-23 | 2027-10-24
Evaluation: 1
Award / order: 1
2027-10-25 | 2027-10-26 | 2027-10-27 | 2027-10-28 | 2027-10-29 | 2027-10-30 | 2027-10-31
Delivery required: 1
Inspection: 1
2027-11-01 | 2027-11-02 | 2027-11-03 | 2027-11-04 | 2027-11-05 | 2027-11-06 | 2027-11-07
Promises: 1 | Promises: 1
Year at a glance
Month | Orders due | Deliveries required | Supplier promises
2027-01-01 | 0 | 0 | 0
2027-02-01 | 0 | 0 | 0
2027-03-01 | 0 | 0 | 0
2027-04-01 | 0 | 0 | 0
2027-05-01 | 0 | 0 | 0
2027-06-01 | 0 | 0 | 0
2027-07-01 | 0 | 0 | 0
2027-08-01 | 0 | 0 | 0
2027-09-01 | 0 | 0 | 0
2027-10-01 | 3 | 2 | 2
2027-11-01 | 0 | 1 | 2
2027-12-01 | 0 | 0 | 0
Formulas:
Tuesday = COUNTIFS(Procurement!$M9:M68,">="&[Monday],Procurement!$M9:M68,"<"&EDATE([Monday],1),Procurement!$C9:C68,"<>",Procurement!$AC9:AC68,"<>Cancelled",Procurement!$B9:B68,IF(D8="All","*",D8))
Wednesday = COUNTIFS(Procurement!$L9:L68,">="&[Monday],Procurement!$L9:L68,"<"&EDATE([Monday],1),Procurement!$C9:C68,"<>",Procurement!$AC9:AC68,"<>Cancelled",Procurement!$B9:B68,IF(D8="All","*",D8))

## Procurement
Procurement plan
60 packages. Replace the examples. Pale purple columns contain formulas. All durations use working days.
Ready-for-use date includes inspection. Supplier lead time starts at award. Enter promises separately in W.
Total packages: 3 |  |  | Active packages: 3 |  |  | Overdue actions: 0 |  |  | Delivery risks: 1
Package information | Package information | Package information | Package information | Planning inputs | Planning inputs | Planning inputs | Planning inputs | Planning inputs | Planning inputs | Target deadlines | Target deadlines | Target deadlines | Target deadlines | Target deadlines | Actual progress and promise | Actual progress and promise | Actual progress and promise | Actual progress and promise | Actual progress and promise | Actual progress and promise | Actual progress and promise | Alerts and status | Alerts and status | Alerts and status | Alerts and status | Alerts and status | Alerts and status | Alerts and status
Package ID | Item / work package | Supplier | Buyer / owner | Ready for use / inspection due | Inspection days | Supplier lead days | Award days | Evaluation days | Tender response days | Delivery required | Award / order by | Evaluation complete by | Tender close / evaluation start | Issue tender by | Tender issued (actual) | Tender closed (actual) | Evaluation done (actual) | Award / order (actual) | Delivered (actual) | Inspected (actual) | Promised delivery | Next action | Action due | Action alert | Delivery alert | Inspection result | Package state | Notes / document URL
EX-01 | Network equipment | Example supplier A | IT buyer | 2027-10-30T00:00:00.000Z | 2 | 10 | 3 | 5 | 10 | 2027-10-28 | 2027-10-14 | 2027-10-11 | 2027-10-04 | 2027-09-20 | 2027-09-11T00:00:00.000Z | 2027-09-25T00:00:00.000Z | 2027-10-02T00:00:00.000Z | 2027-10-09T00:00:00.000Z |  |  | 2027-11-02T00:00:00.000Z | Receive delivery | 2027-10-28 | Planned | Promise after need | Pending | Active
EX-02 | Office furniture | Example supplier B | Facilities buyer | 2027-11-13T00:00:00.000Z | 1 | 15 | 3 | 5 | 10 | 2027-11-12 | 2027-10-22 | 2027-10-19 | 2027-10-12 | 2027-09-28 | [7 empty] | Issue tender | 2027-09-28T00:00:00.000Z | Planned | Awaiting confirmation | Pending | Active
EX-03 | Safety equipment | Example supplier C | Site buyer | 2027-10-16T00:00:00.000Z | 1 | 5 | 2 | 3 | 5 | 2027-10-15 | 2027-10-08 | 2027-10-06 | 2027-10-01 | 2027-09-24 | 2027-09-18T00:00:00.000Z | 2027-09-25T00:00:00.000Z | 2027-10-02T00:00:00.000Z | 2027-10-06T00:00:00.000Z | 2027-10-15T00:00:00.000Z | 2027-10-16T00:00:00.000Z |  | Resolve inspection | 2027-10-16T00:00:00.000Z | Inspection failed | Received | Failed | Active
Formulas:
Target deadlines = IF(OR([Package information]="",COUNT([Planning inputs],[Planning inputs])<2),"",IF([Planning inputs]=0,[Planning inputs],WORKDAY([Planning inputs],-[Planning inputs],Holidays!$B7:B66)))
Target deadlines = IF(OR([Package information]="",COUNT([Target deadlines],[Planning inputs])<2),"",IF([Planning inputs]=0,[Target deadlines],WORKDAY([Target deadlines],-[Planning inputs],Holidays!$B7:B66)))
Alerts and status = IF(OR([Alerts and status]="",[Alerts and status]="Cancelled",[Alerts and status]="Complete",[Alerts and status]="Complete inputs"),"",IF([Alerts and status]="Issue tender",[Target deadlines],IF([Alerts and status]="Close tender",[Target deadlines],IF([Alerts and status]="Complete evaluation",[Target deadlines],IF([Alerts and status]="Award / order",[Target deadlines],IF([Alerts and status]="Receive delivery",[Target deadlines],[Planning inputs]))))))

## Commitments
Supplier commitments
120 additional supplier promises. Keep original dates; revised dates drive the calendar.
Actual completed date closes an item. Cancel commitments separately. Do not repeat delivery promises from Procurement.
Total commitments: 3 |  |  | Completed: 1 |  |  | Overdue: 0 |  |  | Due within 7 days: 0
Deliverable information | Deliverable information | Deliverable information | Deliverable information | Deliverable information | Schedule and revisions | Schedule and revisions | Actuals and actions | Actuals and actions | Actuals and actions | Timing and alerts | Timing and alerts | Timing and alerts | Timing and alerts
Commitment ID | Package ID | Supplier | Commitment / deliverable | Internal owner | Original due | Revised due | Actual completed | State | Chase / next action | Current due | Timing | Days overdue | Original promise
C-01 | EX-01 | Example supplier A | Submit technical drawings | IT buyer | 2027-10-14T00:00:00.000Z |  |  | Open | Chase supplier for drawings | 2027-10-14 | Planned | 0 | Original open
C-02 | EX-02 | Example supplier B | Send finish samples | Facilities buyer | 2027-10-23T00:00:00.000Z | 2027-11-01T00:00:00.000Z |  | In progress | Confirm sample dispatch | 2027-11-01T00:00:00.000Z | Planned | 0 | Revised later
C-03 | EX-03 | Example supplier C | Provide test certificate | Site buyer | 2027-10-10T00:00:00.000Z |  | 2027-10-11T00:00:00.000Z | Open | Certificate received | 2027-10-10T00:00:00.000Z | Completed late | 0 | Completed after original
Formulas:
Timing and alerts = IF([Deliverable information]="","",IF(COUNT([Schedule and revisions])=1,[Schedule and revisions],IF(COUNT([Schedule and revisions])=1,[Schedule and revisions],"")))

## Holidays
Non-working days
Add your holidays and closures. No public holidays are preloaded. Saturdays and Sundays are excluded.
Enter dates in B7:B66. Include prior-year holidays when planning January deadlines. |  | Closure dates entered: 0
Date | Holiday / closure | Quick setup guide
No weekends needed
Saturdays and Sundays are already excluded. Add specific holiday and closure dates.
Use real dates
Enter one date per row. Include prior-year holidays for early January plans.
Plan backwards
The date calculations subtract working days and exclude the dates listed here.

## Resources
Related project templates
Templates from stakeholdermap.com to support your procurement work. Copy a page address below into your browser.
Procurement management plan
Set out what you will buy, how you will select suppliers and who can approve purchases.
https://www.stakeholdermap.com/project-templates/procurement-management-plan-template.php
Decision log
Record supplier selection, contract awards and agreed changes, with the decision owner and date.
https://www.stakeholdermap.com/project-templates/decision-log-template.php
Risk register
Track possible delays, supplier failure and other risks before they affect delivery.
https://www.stakeholdermap.com/risk/risk-register.php
Issue log
Assign an owner and action date when a delivery is late, an inspection fails or a supplier problem needs resolving.
https://www.stakeholdermap.com/project-templates/issue-log.php
Lessons learned template
Record what worked and what to change before the next tender or supplier appointment.
https://www.stakeholdermap.com/project-templates/lessons-learned-template.php
Browse all project templates
Find more planning, reporting and control templates for your project.
https://www.stakeholdermap.com/project-templates/project-management-templates.php