## ACTION ITEMS
PROJECT ACTION ITEMS
PROJECT No: |  | FULL PROJECT NAME: | Orion upgrade |  |  |  | PROJECT MANAGER: | Andrew Smith
ACTION ITEM No. | DATE OPENED | DESCRIPTION | PRIORITY | RESPONSIBLE PARTY | DUE DATE | COMPLETION DATE | PROGRESS NOTES | STATUS
1 | 2018-12-15 | Complete job description for the project assistant. | Medium | Project Manager | 2018-12-31 |  | Awaiting review from the project sponsor. | Open
2 | 2018-12-23 | Finalise the project plan. | High | Project Manager | 2019-01-03 |  | Completed and with the Project Board for approval. | Closed
3 | 2019-01-02 | Book resources for design phase. | Low | Resource Manager |  | 2019-01-21 | Requires PID approval first. | Deferred
4 | 2019-01-03 | Prepare Project Initiation Document. | Low | Project Manager | 2019-03-15 |  |  | Open

## DEFINITIONS
DEFINITIONS
PROJECT No.
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
This Link Takes You to Project No. in the Template
PROJECT MANAGER
Individual responsible for creating, updating and maintaining the integrity of the action items list. Individual assigned with the responsibility of documenting action items and orchestrating updates to the action items list with those responsible and accountable for their assigned action items.
This Link Takes You to Project Manager in the Template
FULL PROJECT NAME
The name or title of the project.
This Link Takes you to the Full Project Name in the Template
ACTION ITEM No.
Give each action a unique ID so that it can be tracked easily and cross referenced for example in a Change Request or a Risk Register. Example: AI01, AI02, AI03…
This Takes You to Action Item No in the Template
DATE OPENED
The date the action was opened, i.e. the date that the project team agreed that the action needs to be completed.
This Link Takes You to Date Opened in the Template
DESCRIPTION
A clear description of the action to be taken along with any relevant cross references e.g. to a change request or risk.
This Link Takes You to Description in the Template
PRIORITY
A simple rating that categorises the importance and/or urgency of the action. "High" denotes High Priority. "Medium" denotes "Medium Priority." "Low" denotes "Low Priority." To change the menu items go to the Data Tab > Data Tools > Data Validation. Select the settings tab and enter the new menu items in the Source: field.
This Link Takes You to Priority in the Template
RESPONSIBLE PARTY
The individual responsible for ensuring that an action item is carried out in the agreed upon manner. This isn't necessarily the person who will actually complete the action, but they will take ownership and accountability for the action.
This Link Takes You to Responsible Party in the Template
DUE DATE
The date the action item is expected to be closed or needs to be closed.
This Link Takes You to Due Date in the Template
COMPLETION DATE
The actual date the action item was closed.
This Link Takes You to Completion Date in the Template
PROGRESS NOTES
Progress of an action item to date. Start with the date, and then briefly describe what has been accomplished. EXAMPLE: "MM/DD/YYYY - Enter Notes."
This Link Takes You to Notes in the Template
STATUS
In this section, please select which action items have been Open (not resolved yet,) Cancelled (No Action Deemed Necessary,) Closed (resolved,) Deferred (put on hold.) To change the menu items go to the Data Tab > Data Tools > Data Validation. Select the settings tab and enter the new menu items in the Source: field.
This Link Takes You to Status in the Template
This template was provided by
https://www.stakeholdermap.com/

## CUSTOMISE
HOW TO CHANGE THE MENU ITEMS IN PRIORITY AND STATUS FIELDS
Default settings
Priority - High, Medium or Low
Status - Open, Cancelled, Completed, Deferred
To change the menu items
To change the menu options or remove the dropdown select Data > Data Validation > Settings
HOW TO CHANGE CELL COLOUR FOR PRIORITY AND DUE DATE
Default settings Priority
Priority High = Red
Priority Medium = Medium
Priority Low = Green
Default settings Due Date
Due Date later than today = Red
Due Date in less than 30 days = Orange
Due Date in more than 30 days = No format
If the Due Date is blank no format is set.
If the completion date is set the Due Date cell will be grey
To change the cell colour
The colour is driven by conditional formatting. To change the colours, edit or remove the formatting select Home > Conditional Formatting > Manage Rules