## Calendar
Project portfolio calendar 2026
Example portfolio. Replace sample inputs in Projects and Milestones. Lavender columns contain formulas.
Portfolio | Business change portfolio |  |  | Review date | 2026-10-24
View month (1–12) | 10 | View year | 2026 | Project ID or All | All
Projects in progress |  | 3 | Overdue milestones |  |  | 2
Open milestones: next 30 days |  | 2 | Input errors across portfolio |  |  | 0
Daily counts: project starts / project finishes / milestones due
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04
Finishes: 1
Milestones: 1
2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11
Starts: 1
Milestones: 1
2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18
Finishes: 1
Milestones: 1
2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25
Milestones: 1
2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01
Milestones: 1
2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08
Starts: 1
Counts show current planned dates, including completed items. Cancelled items and invalid entries are excluded.
Use the Roadmap for project overlap, and filter Projects or Milestones for names, owners and details.
Review date controls overdue flags. It does not restore historical statuses. Enter =TODAY() for a rolling date.
Roadmap shows the full portfolio for the viewing year. The Project ID filter applies only to this Calendar.

## Roadmap
Portfolio roadmap
Current planned project spans by month. Numbers show milestones due in that month, including completed milestones.
Green = On track. Amber = At risk. Red = Off track. Blue = Complete. Cancelled or invalid projects have no shaded span.
Milestone counts can appear outside the project span. Use Projects notes to record dependencies. Overlap does not measure resource capacity.
View year | 2026
Project ID | Project name | Owner | Health | Status | Start | Finish | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
P001 | Customer portal | Alex Morgan | At risk | In progress | 2026-08-03 | 2026-11-20 | 2026-10-01: 2
P002 | Office relocation | Sam Patel | On track | In progress | 2026-09-01 | 2026-12-11 | bar: 2026-01-01 to 2026-12-01
P003 | Finance reporting | Jamie Taylor | Off track | In progress | 2026-07-06 | 2026-10-16 | bar: 2026-01-01 to 2026-12-01
P004 | Service review | Casey Brown | On track | Complete | 2026-06-01 | 2026-10-02 | bar: 2026-01-01 to 2026-12-01
P005 | Supplier onboarding | Robin Green | At risk | On hold | 2026-10-05 | 2027-01-22 | bar: 2026-01-01 to 2026-12-01
P006 | Data platform | Drew Wilson | On track | Planned | 2026-11-02 | 2027-03-26

## Projects
Projects
50 projects. Give every project a unique Project ID. Update status, health and progress at each portfolio review.
Dates are current planned dates. Progress is entered manually. Use notes for dependencies, decisions and resource concerns.
Health: On track / At risk / Off track. Project and milestone alerts calculate from the review date on Calendar.
Project ID | Project name | Programme / area | Project owner | Sponsor | Priority | Status | Health | Planned start | Planned finish | Progress | Alert | Overdue milestones | Dependencies / notes
P001 | Customer portal | Digital | Alex Morgan | Operations director | High | In progress | At risk | 2026-08-03 | 2026-11-20 | 65% | Within dates | 1 | Needs finance interface from P003.
P002 | Office relocation | Workplace | Sam Patel | Finance director | High | In progress | On track | 2026-09-01 | 2026-12-11 | 40% | Within dates | 0
P003 | Finance reporting | Finance | Jamie Taylor | Finance director | Medium | In progress | Off track | 2026-07-06 | 2026-10-16 | 80% | Finish overdue | 1
P004 | Service review | Operations | Casey Brown | Operations director | Medium | Complete | On track | 2026-06-01 | 2026-10-02 | 100% | Complete | 0
P005 | Supplier onboarding | Procurement | Robin Green | Commercial director | Low | On hold | At risk | 2026-10-05 | 2027-01-22 | 10% | On hold | 0 | Awaiting supplier decision.
P006 | Data platform | Digital | Drew Wilson | Technology director | High | Planned | On track | 2026-11-02 | 2027-03-26 | 0% | Within dates | 0

## Milestones
Portfolio milestones
200 milestones. Link each milestone to a unique Project ID. Use one row per decision, delivery, go-live or other key date.
Positive date change means later than baseline. Complete milestones need an actual completion date. Keep formula columns intact.
Calendar included: 1 means shown. Cancelled projects or milestones and invalid milestone entries are excluded.
Milestone ID | Project ID | Milestone / decision | Type | Owner | Baseline due | Current due | Actual completion | Status | Date change (days) | Alert | Project name | Project status | Calendar included | Evidence / dependencies
M001 | P001 | Design approved | Approval | Alex Morgan | 2026-10-09 | 2026-10-09 | 2026-10-09 | Complete | 0 | Complete | Customer portal | In progress | 1
M002 | P001 | UAT sign-off | Approval | Alex Morgan | 2026-10-20 | 2026-10-22 |  | In progress | 2 | Overdue | Customer portal | In progress | 1
M003 | P002 | Lease confirmed | Decision | Sam Patel | 2026-10-26 | 2026-10-26 |  | Planned | 0 | Upcoming | Office relocation | In progress | 1
M004 | P003 | Reporting live | Go-live | Jamie Taylor | 2026-10-16 | 2026-10-16 |  | Blocked | 0 | Overdue | Finance reporting | In progress | 1
M005 | P004 | Review accepted | Delivery | Casey Brown | 2026-10-02 | 2026-10-02 | 2026-10-02 | Complete | 0 | Complete | Service review | Complete | 1
M006 | P005 | Supplier decision | Decision | Robin Green | 2026-11-06 | 2026-11-13 |  | Planned | 7 | Upcoming | Supplier onboarding | On hold | 1
M007 | P006 | Platform go-live | Go-live | Drew Wilson | 2027-03-26 | 2027-03-26 |  | Planned | 0 | Upcoming | Data platform | Planned | 1

## Resources
Related project templates
stakeholdermap.com
Milestone calendar
Plan detailed dates and milestone ownership.
https://www.stakeholdermap.com/project-templates/milestone-calendar-template.php
Governance and approval calendar
Coordinate decision meetings and submission deadlines.
https://www.stakeholdermap.com/project-templates/governance-approval-calendar-template.php
Cost and payment calendar
Plan costs, payment deadlines and outstanding balances.
https://www.stakeholdermap.com/project-templates/cost-payment-calendar-template.php
Testing and release calendar
Coordinate test windows and release readiness.
https://www.stakeholdermap.com/project-templates/testing-release-calendar-template.php
Launch and cutover calendar
Organise deployment and rollback steps.
https://www.stakeholdermap.com/project-templates/launch-cutover-calendar-template.php
All project templates
Browse the full collection of project templates.
https://www.stakeholdermap.com/project-templates/project-management-templates.php