## Calendar
Testing & release calendar 2026
Plan test windows, sign-off deadlines and releases. Replace the sample entries in Tests and Releases.
Project | Example project |  |  | Review date | 2026-10-23
View month (1–12) | 10 | View year | 2026
Overdue test windows |  | 1 | Overdue sign-offs |  |  | 0
Ready to release |  | 0 | Overdue releases |  |  | 0
Daily counts: test windows / tests ending / sign-offs due / planned releases
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04
|  |  | Tests: 1 | Tests: 1
Ending: 1
2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11
Tests: 1 | Tests: 1 | Tests: 1 | Tests: 1 | Tests: 1
Ending: 1
Sign-offs: 1
Releases: 1
2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18
Tests: 1 | Tests: 1 | Tests: 1 | Tests: 1 | Tests: 1
Ending: 1
2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25
|  |  | Tests: 1 | Tests: 1 | Tests: 1 | Tests: 1
Sign-offs: 1
2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01
Tests: 1
Ending: 1
Releases: 1
2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08
Tests: 1 | Tests: 1 | Tests: 1 | Tests: 1 | Tests: 1
Ending: 1
Test windows include both start and finish dates. Cancelled tests are excluded. Counts show scheduled dates.
Use Tests and Releases for names, owners and status. Review date controls overdue flags, not historical status.
Set the review date for each review, or enter =TODAY(). Formula columns have a lavender fill.

## Tests
Test windows
100 test windows. Link each window to a unique Release ID from Releases. Keep completed windows for reference.
One row per test phase or retest. Passed requires an actual finish date and an evidence reference.
Test ID | Release ID | Test window / scope | Test type | Owner | Planned start | Planned finish | Status | Actual finish | Evidence / notes | Alert
T001 | R001 | Integration testing | Integration | Test lead | 2026-10-05 | 2026-10-09 | Passed | 2026-10-09 | Test report IT-001 | Complete
T002 | R001 | User acceptance testing | UAT | Business lead | 2026-10-12 | 2026-10-16 | In progress |  | Two scenarios remain | Overdue
T003 | R001 | Regression retest | Regression | Test lead | 2026-10-22 | 2026-10-26 | Planned |  | Retest after defect fixes | On schedule
T004 | R002 | Security verification | Security | Security lead | 2026-11-02 | 2026-11-06 | Planned |  |  | On schedule
T005 | R003 | Maintenance smoke test | Smoke | Service owner | 2026-10-01 | 2026-10-02 | Passed | 2026-10-02 | Smoke report SM-003 | Complete

## Releases
Releases & sign-off
50 releases. Sign-off deadline = planned release date minus lead days. Lead days are calendar days, including weekends.
Ready requires linked tests, all passed or cancelled, no input errors, zero critical defects and approval. No tests means not ready.
Enter zero critical defects explicitly. Record the actual release date after deployment. Status reflects the latest entries.
Release ID | Release / version | Release owner | Planned release | Sign-off lead days | Sign-off deadline | Decision owner | Approval | Actual release | Open critical defects | Linked tests | Tests remaining | Readiness | Alert | Decision / release notes
R001 | Customer portal 1.0 | Release manager | 2026-10-30 | 5 | 2026-10-25 | Sponsor | Pending |  | 2 | 3 | 2 | Testing incomplete | On schedule
R002 | Security update | Service owner | 2026-11-13 | 3 | 2026-11-10 | Security owner | Pending |  | 0 | 1 | 1 | Testing incomplete | On schedule
R003 | Maintenance 0.9 | Service owner | 2026-10-08 | 2 | 2026-10-06 | Service owner | Approved | 2026-10-08 | 0 | 1 | 0 | Released | Complete
Formulas:
Sign-off deadline = IF(OR(NOT(ISNUMBER([Planned release])),NOT(ISNUMBER([Sign-off lead days]))),"",[Planned release]-[Sign-off lead days])

## Resources
Related project templates
stakeholdermap.com
Project management templates
Browse project planning and delivery templates.
https://www.stakeholdermap.com/project-templates/project-management-templates.php
Issue log
Track defects, blockers and actions.
https://www.stakeholdermap.com/project-templates/issue-log.php
Decision log
Record release and sign-off decisions.
https://www.stakeholdermap.com/project-templates/decision-log-template.php
Governance and approval calendar
Schedule approval meetings and submission deadlines.
https://www.stakeholdermap.com/project-templates/governance-approval-calendar-template.php
Launch and cutover calendar
Plan deployment steps and rollback actions.
https://www.stakeholdermap.com/project-templates/launch-cutover-calendar-template.php
Procurement and supplier calendar
Coordinate supplier dependencies and delivery dates.
https://www.stakeholdermap.com/project-templates/procurement-calendar-template.php